⭐ THE GrowthOS PLAYBOOK ⭐

The MSP Sales & Marketing Foundation

Implementation Timeline & Readiness Requirements

The full implementation of this playbook — all 4 phases and 14 steps — is designed as a 12-month roadmap. This allows time for proper setup, nurturing, optimization, and compounding results across SEO, GEO, outbound, authority building, and SDR execution.

However, because many of these activities can be accelerated with the right resources, the entire plan can be compressed into as little as 4–6 months. The more aligned your team is, the faster the system produces measurable results.

🚦 Before You Begin — STOP.

Nothing in this playbook will work unless you have two foundational assets in place:

1. A functioning website

Your website is the digital home base for SEO, GEO, content, conversion, and outbound alignment. Without it, every other step collapses.

2. A written Ideal Client Profile (ICP)

Your ICP must pass two non-negotiable tests:

- Do YOU want to do business with them? If you don’t enjoy serving them, you won’t market well to them.

- Will THEY choose your company when given the opportunity? If the answer is no, the entire funnel becomes friction.

If your ICP passes both tests, you’re ready.

🚀 Now You Can Execute the 4–14 Plan

Follow these 4 phases and 14 steps to build a predictable, repeatable, scalable flow of new clients. This is the MSP Sales & Marketing Foundation — the system that transforms random growth into reliable growth.

🚀 PHASE 1 — FOUNDATION & VISIBILITY

Goal: Establish visibility, fix discoverability gaps, and build the baseline for outbound.

1. SEO — Search Engine Optimization

GrowthOS Dashboard

- SEO status report

- SEO suggestions/fixes list

- SEO strategy progress tracker (current quarter goals/tasks/priorities)

Duties

- Full SEO audit (technical, on-page, off-page)

- Keyword strategy aligned to ICP

- On-page optimization (titles, headers, metadata, internal links)

- Technical SEO fixes (speed, indexing, schema, mobile)

- Backlink strategy (authority building)

- Local SEO optimization (GBP, citations, NAP consistency)

- Monthly SEO reporting & insights

KPIs

- +20–40% increase in organic traffic by Month 3

- +10–20 new ranking keywords per month

- +1–2 Domain Authority improvement per quarter

- 80% reduction in technical SEO errors

- Top 3 ranking for 3–5 core service keywords by Month 6

2. GEO — Generative Engine Optimization

Responsible: Claude, Lance & Vernon

GrowthOS Dashboard

  - GEO status report

  - GEO suggestions/fixes list

  - GEO strategy progress tracker (current quarter goals/tasks/priorities)

Duties

- Structure content for AI parsing (headings, bullets, FAQs)

- Implement schema markup (LocalBusiness, Service, FAQ, Reviews)

- Quarterly content refresh for AI accuracy

- Optimize for AI engines (ChatGPT, Perplexity, Google AI Overviews, Bing AI)

- Monitor AI citations and summary accuracy

- Improve local GEO visibility (GEO grids, GBP optimization)

- Publish authoritative, fact-based content AI engines can cite

- Correct AI inaccuracies with targeted content updates

KPIs

- AI citation frequency: +10–20% MoM

- AI summary accuracy: 85–95%

- GEO grid visibility: 60–80% green zones

- Schema coverage: 100% of service pages

- Content freshness: 80% of pages updated in last 90 days

- GBP engagement: +15–25% MoM

3. Blogging & Content Development

Responsible: Claude & Lance

Duties

- Monthly blog calendar

- 2–4 SEO + GEO optimized blogs

- Industry-specific, ICP-aligned content

- Internal linking to service pages

- AI-friendly formatting (definitions, lists, FAQs)

KPIs

- 2–4 blogs published monthly

- +10–20% increase in organic blog traffic

- 1–2 inbound leads per month from content

- 5–10 new keywords ranking per blog

4. Social Media Posting & Connections

Duties

- Weekly posting schedule

- AI-personalized content

- LinkedIn connection strategy

- Thought leadership posts

- Engagement with ICP prospects

KPIs

- 8–12 posts per month

- +50–100 new LinkedIn/X/FB connections monthly

- +10–20% increase in engagement

- 1–3 inbound conversations per month

5. Website Oversight & Optimization

Responsible: Claude & Lance

Duties

- UX review & improvements

- Conversion optimization (CTAs, forms, layout)

- Landing page creation

- Form optimization & testing

- Speed and mobile performance improvements

KPIs

- Increase website conversion rate to 2–4%

- Reduce bounce rate by 10–20%

- Launch 1–2 new landing pages per month

- +10–15% increase in time on page

🔥 PHASE 2 — PIPELINE & OUTBOUND ENGINE

Goal: Build predictable outbound pipeline and define the ICP.

6. ICP Development & Targeting Strategy

Duties

- Define ICPs (industry, size, tech stack, geography)

- Pain point mapping

- Messaging alignment

- Value proposition refinement

KPIs

- ICP finalized by Month 1

- 3–5 ICP-specific messaging frameworks created

- 20% increase in outbound response rates

7. List Building & Data Acquisition

Duties

- Prospect list creation

- Data enrichment & scrubbing

- Intent data integration (SniperLeads)

- Segmentation by ICP

KPIs

- 500–1,500 new contacts added monthly

- 90%+ email deliverability

- 10–15% of list showing intent signals

8. Email Campaigning & Nurture Sequences

Duties

- Cold outreach sequences

- Warm nurture sequences

- A/B testing

- Deliverability optimization

- Personalization at scale

KPIs

- 40–60% open rate

- 8–15% reply rate

- 2–5 meetings booked per month

Estimated Monthly Budget: CRO Leader + SDR

9. CRM Administration & Optimization

Duties

- Pipeline configuration

- Automation setup

- Reporting dashboards

- Data hygiene

- Lifecycle stage definitions

KPIs

- 95%+ data accuracy

- 100% of opportunities in correct stages

- Weekly reporting delivered on time

10. Opportunity Pipeline Metrics & Oversight

Duties

- Stage definitions

- Conversion tracking

- Deal velocity reporting

- Forecasting

KPIs

- Weekly stage-to-stage conversion tracking

- 10–20% improvement in deal velocity

- 100% of active deals updated weekly

🏆 PHASE 3 — AUTHORITY, TRUST & DEMAND CREATION

Goal: Build credibility and increase inbound demand.

11. Reviews & Testimonies

Responsible: Lance & Vernon

Duties

- Review acquisition program

- Testimonial collection

- Case study development

- Video testimonials (optional)

KPIs

- 3–5 new Google reviews per month

- 1 new case study per quarter

- 4–6 testimonials collected per quarter

12. Events (Virtual & In-Person)

Responsible: Lance & Vernon

Duties

- Event selection (webinars, tradeshows, lunch & learns)

- Booth strategy & materials

- Pre-event outreach

- Post-event follow-up sequences

KPIs

- 1–2 events per quarter

- 20–50 leads per event

- 3–5 meetings booked per event

⚡ PHASE 4 — SDR OUTREACH & SALES EXECUTION

Goal: Build consistent outbound activity and convert intent into meetings.

13. SDR Outreach (Internal or Outsourced)

Responsible: CRO Leader Team, SDR & Vernon

Duties

- Cold calling

- Follow-up calls

- Appointment setting

- Script development

- Daily activity tracking

KPIs

- 40–80 calls/day

- 5–10 conversations/day

- 12–24 meetings booked per quarter

- 20–30% show rate improvement

14. Sales Enablement & Support

Responsible: CRO Leader Team & Vernon

Duties

- Scripts

- Objection handling

- Proposal templates

- Follow-up sequences

- Competitive positioning

KPIs

- 100% of reps using approved scripts

- 20% improvement in close rate

- 100% of proposals delivered within 48 hours

The GrowthOS KPI dashboard: